## Sheet6
Data Base Creation | Anusha | Mockups | Hrishikesh
| Nikitha |  | Elaine
| Pavitra |  |  | Kavya | Split School
User Management | Mathias | contact us
Upload New .CSV Data (Admin User) | Manjiri | legal disclaimer
school | Apoorva | Create peer
instructiona;l | Tulasi
non instr | Anson |  |  | Migration - Elaine | 5.3 to 5.4
employee | Hrishikesh
finance | Kavya
private | Elaine
non profit
public
default rate
admissions
application details
unduplicated head count
graduation
ug credit hours
aplication details

## Release Plan
Sprint # | Epic # | Epic/Features | Number of Hours | Duration
0 | 1 | Gather and prioritize features and stories from client
| 2 | Develop a release plan and initial estimate of work for SOW |  |  | Done
| 3 | Develeopment Statement of Work
| 4 | Create Integration environment and common code repository
1 | 8 | Register
| 9 | Login / Authentication
| 10 | Reset Password
| 21 | Upload New .CSV Data (Admin User)
| 25 | User Management
2 | 18 | Comments
| 11 | Peer Groups
3 | 14 | Save Visualization
Data Visualization
| 24 | Usage Statistic Reports
4 |  | Legal Disclaimers
Website Traffic Report
Print Visualization
5 |  | Contact Us
Search Engine Optimization
| 7 | Navigation Instructions
6 |  | Testing
Documentation

## Stories
Feature # | Story No. # | Story Description “As a <role>, I want to <action>, to achieve <business value>” | Priority | Dependency | Story Points | Release # | Iteration # | "Done" Criteria (include the criteria which determine when a story is "done")
6 | 6.1 | As a Product Owner, I want concise text so that users can quickly skim the website and still understand how to access the functionality they seek. | 4 - Nice to Have | none | 3
| 6.2 | As a Product Owner, I want a well thought out color palette to reflect the quality UNO brand. | 4 - Nice to Have | none | 3
| 6.3 | As a Product Owner, I want a font and font size that is easy to read online so that users can easily read the website's content. | 4 - Nice to Have | none | 3
| 6.4 | As a Product Owner, I want high-quality images and graphics so that my website looks professional. | 4 - Nice to Have | none | 3
| 6.5 | As a Product Owner, I want a simple and consistent navigation scheme so that users can quickly access the functionality they seek. | 4 - Nice to Have | none | 3
| 6.6 | As a Product Owner, I want logical and easy-to-understand page names so that users can quickly access the functionality they seek. | 4 - Nice to Have | none | 2
| 6.7 | As a Product Owner, I want the website navigation to follow a logical hierarchical page structure so users can easily move around between pages. | 4 - Nice to Have | none | 3
| 6.8 | As a Product Owner, I want a navigation bread crumb so users can easily move around between pages. | 4 - Nice to Have | none | 5
| 6.9 | As a Product Owner, I want the website to follow the "three-click" rule so that users can access the functionality they need quickly. | 4 - Nice to Have | none | 5
| 6.10 | As a Product Owner, I want all webpages to use a grid based layout that arranges content into sections, columns and boxes that line up and feel balanced so that users can easily find content on a webpage. | 4 - Nice to Have | none | 5
| 6.11 | As a Product Onwer, I want webpages to use an "F-screen" pattern layout so that information is displayed in order of importance (left to right and top to bottom) so that the layout aligns with users' natural behavior. | 4 - Nice to Have | none | 3
7 | 7.1 | As a Guest or Registered User, I want navigation instructions to be displayed when I hover over a clearly marked area in the right margin of the webpage so that I can get navigation instructions. | 3 - Medium | 2013-08-11 | 5
| 7.2 | As a Guest or Registered User, I want navigation instructions built into the webpage so that the user understands how to use the webpage | 3 - Medium | 2013-08-11 | 5
| 7.3 | As a Guest or Registered User, I want the navigation instructions to explain how to access the most commonly used features. | 3 - Medium | 2013-08-11 | 3
8 | 8.1 | As a Guest User, I want the option to register with the website so that I can obtain access to Registered User functionality. | 2 - High | none | 2
| 8.2 | As a Product Owner, I want to have email, password, and affiliation type in order to register so that only the minimum amount of information needed is collected from the user. | 2 - High | none | 1
| 8.3 | As a Product Owner, I want to have all the passwords to be encrypted to protect from unauthorized usage of data | 2 - High | none | 1
9 | 9.1 | As a Product Owner, I want Registered Users to use their email and password to login to the website so that the user can be authenticated. | 2 - High | 8 | 1
10 | 10.1 | As a Registered User, I want the option to change my password so that I can manage my credentials. | 2 - High | 2017-08-09 | 1
11 | 11.1 | As a Guest or Registered User, I can select one or more universities to compare, to achieve a subset of universities that have value to my organization. | 1 - Critical | 21 | 5
| 11.2 | As a Registered User, I can save the selected universities list as a Peer Group in my account, to achieve a repeatable search. | 1 - Critical | 21 | 8
| 11.3 | As a Guest or Registered User, I can select multiple parameters (IPEDS "special characteristics") to filter the list of universities, to achieve a discovery tool. | 1 - Critical | 21 | 8
| 11.4 | As a Registered User, I can save the parameter selections as a Peer Group in my account, to achieve a repeatable search. | 1 - Critical | 21 | 8
| 11.5 | As a Registered User, I can select a saved Peer Group from my list, to view results of a previous search. | 1 - Critical | 21 | 5
12 | 12.1 | As a Registered User, I can share a saved Peer Group with another Registered User, to achieve collaboration. | 4 - Nice to Have | 21, 11 | 13
13 | 13.1 | As a Guest or Registered User, I can view a scatterplot of all of the available data for a specific year, to achieve an overall understanding. | 1 - Critical | 21, 11 | 8
| 13.2 | As a Guest or Registered User, I can view a scatterplot of a subset of the universities, for a specific year, to achieve a visual representation. | 1 - Critical | 21, 11 | 8
| 13.3 | As a Guest or Registered User, I can select the performance (y-axis) and resource parameters (x-axis) for the scatterplot, to view the metrics of interest to me. | 1 - Critical | 21, 11 | 8
| 13.4 | As a Guest or Registered User, I can view a table of numeric parameters for a subset of universities, to compare metrics in a group of universities. | 1 - Critical | 21, 11 | 8
| 13.5 | As a Guest or Registered User, I can sort the table by certain numeric parameters, to achieve a comparison on a desired parameter. | 1 - Critical | 21, 11 | 8
| 13.6 | As a Guest or Registered User, I can see the universities grouped into top third, middle, and bottom third, to quickly get a sense of the range. | 1 - Critical | 21, 11 | 8
| 13.7 | As a Guest or Registered User, I can see the average data for universities in the top third, middle, and bottom third, to quickly get a sense of the range. | 1 - Critical | 21, 11 | 8
| 13.8 | As a Guest or Registered User, I can view a tabular summary of the scatterplot data for a chosen university, to quickly see the metrics for one point. | 1- Critical | 21, 11 | 5
| 13.9 | As a Guest or Registered User, I can view a full summary of the available data for a chosen university, to view independently from other universities. | 1 - Critical | 21, 11 | 5
14 | 14.1 | As a Registered User, I can save the Peer Group along with the performance, resource, year and other parameters, to achieve a repeatable View. | 2 - High | 21, 11, 13 | 13
| 14.2 | As a Registered User, I can select a saved View to load, to achieve a repeatable analysis. | 2 - High | 21, 11, 13 | 8
15 | 15.1 | As a Guest or Registered User, I can print the visualizations, to preserve a static version of my analysis. | 2 - High | 21, 11, 13 | 8
16 | 16.1 | As a Guest or Registered User, I can export the table data to Excel. | 4 - Nice to Have | 21, 11, 13 | 5
17 | 17.1 | As a Registered User, I want the website to automatically log me out after 60 minutes of inactivity in case I forget to log out manually to prevent another person from using my login credientials. | 4 - Nice to Have | 9 | 5
| 17.2 | As an Admin User, I want the website to automatically log me out after 10 minutes of inactivity in case I forget to log out manually, to prevent another person from using my login credientials. | 4 - Nice to Have | 9 | 5
18 | 18.1 | As a Registered User, I want to be able to leave a comment on the website to share my opnions. | 3 - Medium | 9 | 5
| 18.2 | As a Registered User, I want a display to inform me that my comment will be reviewed by an Admin User before it is posted so that I understand why my comment doesnt immediately display. | 3 - Medium | 9 | 5
| 18.3 | As a Registered User, I want an email letting me know when someone has replied to my comment so that I can see what others have to say about my comment. | 3 - Medium | 9 | 5
| 18.4 | As a Registered User, I want to reply to others' comments on the website to share my opinion. | 3 - Medium | 9 | 5
| 18.5 | As an Admin User, I want an email letting me know when someone has added a new comment so that I can the approprieatness of the comment before it is posted to the public. | 3 - Medium | 9 | 5
| 18.6 | As an Admin User, I want the option to approve or deny a new comment. | 3 - Medium | 9 | 5
| 18.7 | As an Admin User, when I approve a new comment, I also want the option to reply to that comment as well so that I can address any questions or concerns before it is made public. | 3 - Medium | 9 | 5
| 18.8 | As an Admin User, when I deny a new comment, I want the comment to be removed from the system so that inappropreiate material is not posted to the public. | 3 - Medium | 9 | 5
19 | 19.1 | As a Product Owner, I want to display my phone number to the public so that anyone can call me. | 2 - High | none | 3
| 19.2 | As a Product Owner, I want to display my email to the public so that anyone can email me. | 2 - High | none | 2
| 19.3 | As a Product Owner, I want to display address to the public so that anyone can mail me. | 2 - High | none | 3
20 | 20.1 | As a Product Owner, I want to display my terms and conditions to prevent the public from misusing the website and website data. | 2 - High | none | 3
| 20.2 | As a Product Owner, I want to display my privacy policy to inform the public of how the data generated from this website will be used so that users are comfortable providing data. | 2 - High | none | 3
| 20.3 | As a Product Owner, I want users to acknowledge my terms and conditions before completing the user registration process. | 2 - High | none | 5
| 20.4 | As a Product Owner, I want users to acknowledge my privacy policy before completing the user registration process. | 2 - High | none | 5
21 | 21.1 | As an Admin User, I want to navigate my local machine and select the file I wish to upload so that I can make that file available to the website. | 1 - Critical | 9 | 3 |  |  | If I am an admin, I can navigate my local machine and select the file I wish to upload.
| 21.2 | As an Admin User, I want to upload one or more selected IPEDS .csv files so that the website can use it for data visualization features. | 1 - Critical | 9 | 5 |  |  | If I am an admin, I can upload the .csv files.
| 21.3 | As an Admin User, I want to upload one or more selected Loan .csv files so that the website can use it for data visualization features. | 1 - Critical | 9 | Save to database -- Edit the story --- How many rows were saved successfully , failed update/upload |  |  | If I am an admin, I can upload the loan and other .csv files.
|  | Schedule JObs for CSV upload to db |  |  | 2
|  | Cancel Schedule jobs which havent started the upload |  |  | 1
| 21.4 | As an Admin User, I want to confirm or cancel the upload before the .csv file is uploaded to make sure I didnt select the wrong file by mistake. | 1 - Critical | 9 | 2 |  |  | If I am an admin, I can cancel or confirm the upload process.
| 21.5 | As an Admin User, when I confirm the .csv upload, I want the webpage to display a confirmation that the data validation was successful. | 1 - Critical | 9 | 1 |  |  | If I am an admin, I can view a confirmation message on the webpage.
| 21.6 | As an Admin User, when I cancel the scheduled job for .csv upload, I want the webpage to display a confirmation that the upload was canceled. | 1 - Critical | 9 | 5 |  |  | If I am an admin, I can view a cancelled upload message on the webpage.
| 21.7 | As a Product Owner, I want the ability to execute an SQL query to remove all records associated with a specific .csv upload so that I can resolve an issue with a specific .csv upload. | 4 - Nice to have | 9 | 8 |  |  | If I am a product owner, I can execute the SQL query to remove all records associated with a specific .csv file.
22 | 22.1 | As an admin, I want to put the website in maintenance mode (redirect to a maintenance message). | 2 - High | 9 | 13
| 22.2 | As an admin, I want to provide admin access to selected users to be able to work on the website. | 2 - High | 9 | 8
| 22.3 | As an admin, I should be able to notify the users when the website is under maintainance to keep them informed. | 2 - High | 9 | 8
| 22.4 | As an admin, I should be able to take a backup on regular time intervals to restore data in case of disaster. | 2 - High | 9 | skip
| 22.5 | As an admin, I want to provide role based access to users to protect the data from being misused. | 2 - High | 9 | 8
| 22.6 | As an admin, I should be able to deploy the code changes to keep the application up-to-date. | 2 - High | 9
23 | 23.1 | As an admin, I want to get the report of traffic on the website to analyse the flow of users. | 2 - High | 9 | 13
| 23.2 | As an admin, I want to track the geo-locations of the user to provide even better statistics to the users. | 2 - High | 9 | 8
| 23.3 | As an admin, I want to restrict the accessibility of website to certain locations to avoid wrong usage of data. | 2 - High | 9 | skip
| 23.4 | As an admin, I want to save the reports of traffic on a daily, weekly and monthly basis to analyse the traffic on the website. | Nice to have? | 9 | 5
24 | 24.1 | As an admin, I should be able to query the number of users registered so that I can track website usage. | 2 - High | 9 | 5
| 24.2 | As an admin, I should be able to track how many public peer groups are being used so as to improve the business by creating more public peer groups | 2 - High | 9 | 13
| 24.3 | As an admin, I should be able to view the count of parameters used to create the private peer groups to determine if new public peer groups should be created. | 2 - High | 9 | 8
| 24.4 | As an admin, I should be able to download the Registered Users table to track the types of users who use the website. | 2 - High | 9 | 2
25 | 25.1 | As an admin, I should be able to view all the Registered and Admin Users so that I can manage users. | 2 - High | 9 | 2
| 25.2 | As an admin, I should be update Admin User information so that i can maintain up-to-date user information. | 2 - High | 9 | 1
| 25.3 | As an admin, I should be able to delete users so that I can manage website access. | 2 - High | 9 | 1
| 25.4 | As an Admin, I wish to see a message confirming the delete, to prevent accidental deletion. |  |  | 1
| 25.5 | As an admin, I should be able to filter the list of users to view only the Admin Users so that I can easily manage Admin Users. | 2 - High | 9 | 1
26 | 26.1 | As the product owner, I want to have keywords inserted in the meta description of the website to optimize the website for search engines(Google,Bing, Yahoo). | 3 - Medium | 6 | 8
27 | 27.1 | As the product owner, I want to integrate the website with third-party to generate revenue from ads. | 4 - Nice to Have | none | 8
28 | 28.1 | As an Admin User, I want to upload revisions to the .csv files so that I can keep the website data up-to-date. | 4 - Nice to Have | 21 | 13
| 28.2 | As an Admin User, I want the software to compare the .csv file to the existing database and apply the correct additions and edits to the existing database. | 4 - Nice to Have | 21 | 8
[5 empty] | 439 | total of all required and nice to have

## Feature
Feat # | Feature Description | Size | Dependency | Priority | User Story Assignment
1 | Gather and prioritize features and stories from client
2 | Develop a release plan and initial estimate of work for SOW
3 | Development Statement of Work
4 | Create Integration environment and common code repository
5 | Create Data model and Sprint Planning based on requirements
6 | Public Landing Page | 3 | none | 4 - Nice to Have | Mathias
7 | Navigation Instructions | 2 | yes - 8, 11, 13 | 3 - Medium | Mathias
8 | Register | 1 | none | 2 - High | Mathias | 1
9 | Login / Authentication | 1 | yes - 8 | 2 - High | Mathias
10 | Reset Password | 3 | yes - 8, 9 | 2 - High | Mathias
11 | Peer Groups | 8 | yes - 21 | 1 - Critical | Elaine | 2 | 74
12 | Share Peer Group | 5 | yes - 11 | 4 - Nice to Have | Elaine
13 | Create Visualization | 8 | yes - 11 | 1 - Critical | Elaine | 2
14 | Save Visualization | 3 | yes - 13 | 2 - High | Elaine
15 | Print Visualization | 3 | yes - 13 | 2 - High | Elaine
16 | Export Visualization | 2 | yes - 13 | 4 - Nice to Have | Elaine
17 | Session Time Out | 1 | yes - 9 | 4 - Nice to Have | Mathias
18 | Comments | 5 | yes - 9 | 3 - Medium | Mathias |  | 60
19 | Contact Us | 1 | none | 2 - High | Mathias
20 | Legal Disclaimers | 1 | none | 2 - High | Mathias
21 | Upload New .CSV Data (Admin User) | 8 | yes - 9 | 1 - Critical | Mathias
22 | Website Maintenance (Admin User) | 5 | yes - 9 | 2 - High | Apoorva |  | 75
23 | Website Traffic Report (Admin User) | 5 | yes - 9 | 2 - High | Apoorva
24 | Usage statistics (Admin User) | 8 | yes - 9 | 2 - High | Apoorva |  | What do we consider the base level of analytics for the queries? | Develop the sense of usage. | What numbers do we need to know to justify the project??
25 | User Management (Admin User) | 3 | yes - 9 | 2 - High | Apoorva
26 | Search Engine Optimization | 3 | yes - 6 | 3 - Medium | Apoorva
27 | Revenue Generator | 3 | none | 4 - Nice to Have | Apoorva
28 | Upload Revised .CSV Data (Admin User) | 5 | yes - 21 | 4 - Nice to Have | Mathias
29 | Training
30 | Load Testing and Integration Testing |  |  |  | Run reports on traffic usuage
31 | Deployment |  |  |  | Review comments and reply
32 | Documentation

## Old-Stories
Feature # | Story No. # | Story Description “As a <role>, I want to <action>, to achieve <business value>” | Comments | Priority | Tasks | Dependency | Story Points | Release # | Iteration # | "Done" Criteria (include the criteria which determine when a story is "done")
1 | 0 | NF - Meet with client and gather prioritize requirements |  |  | Develop list of initial user requirements and format as stories
Develop screen mockups of propose
Meet with client and review mockups to confirm requirements
2 | 0 | NF -Develop a project release plan |  |  | From requirements and mockups, develop all the remaining non-functional stories for project
Create story points for all stories
Create tasks and estimates for work effort for all tasks
Develop proposed release plan based on priorities using 3 week sprint and a team of 5 dedicated resources
3 | 0 | NF -Develop estimates for all costs associated with project
| 0 | NF -Develop a statement of work for the project |  |  | Analyse the functionalities to be delivered
Document the features,stories and tasks
Meeting with client an seek sign off of the stetement of work
4 | 0 | NF-Create Integration environment and common code repository |  |  | Create Integration environment
Create Common Code repository
5 | 0 | NF-Create Data model based on requirements |  |  | Develop use case diagrams after establishing the actors (usually people who use the system) and the actions they perform
Develop the data model to design the database
6 | 1 | As a user, I wish to see a landing page (home page) that summarizes the purpose of the site. | Accomplishing landing page , no features |  | Create a landing page that is sparse but information-rich. |  | 1
6 | 2 | As a user, I wish to have a clear understanding of the functions offered to me, at a glance. |  |  | Provide box or other side graphic with a succinct overview (e.g. "1. View performance vs resource data for all reporting universities! 2. Compare your university with a peer group! 3. Save your views and print your findings!") | Other Pages | 3
6 | 3 | As a user, I wish to know which functions are available without registration and which require it. | Nice to have |  | Provide a note ("Registration required to save peer groups.") |  | 1
6 | 4 | As a user, I wish to have a login on the landing page. |  |  | Provide email and password entry (and "remember user name" checkbox?). |  | 2
6 | 5 | As a user, I wish to be able to navigate easily to different pages to perform different functions |  |  | Provide more than one link that goes directly to the analysis page. |  | 3
6 | 6 | As a user, I wish to be able to bookmark the analysis page. |  |  | Ensure analysis hyperlink is directly accessible and does not require auth. |  | 1
7 | 0 | As a user I should be able to register to the website to become a registered user |  |  | Develop UI and logic for the webpage |  | 5
Allow user to have access to register
unit testing the code
7 | 1 | As a registered user/ Admin I should be able to log into the website to access it |  |  | Develop UI and logic for the webpage |  | 5
Allow user ro provide their credentials to login
unit testing the code
7 | 2 | As a registered user/Admin I should be able to reset my password so that I can continue using the website |  |  | Provide registered user the option of resetting their password
Save the new password into the database
unit testing the code
| 3 | As a registered user/Admin I should be able to recover my password so that I can continue using the website |  |  | provide user the option of recovering their password
Email the 'Password reset link' to the user
Allow user to reset the password
unit testing the code
8 | 0 | As a Admin I want to provide proper level of authentication for a user to access the website |  |  | Allow guest user to have access to view basic website |  | 8
[5 empty] | Should be able to view the admin home page. |  | 8
Provide login feature for users.
Should be able to create other Admin
Perform unit testing with test cases and logs.
Load code to test environment
Perform Quality Assurance check with test cases and reports.
Implement code into Integration testing environment.
8 | 1 | As a registered user, I should be able to navigate easily to perform different functions |  |  | Should be able to login to the website.
Should be able to reset the password
Should be able to save and load the custom peer groups
Should be able to post comments
Should be able to download the saved statistics
Should be able to print the saved statistics
9 | 1 | As an Admin User, I want to upload a .csv file so that all users have access to up-to-date data.
10 | 0 | As a DB developer, I should be able to design the database so that I can accommodate the data as per data model |  |  | Design the database using physical data model | Data Model |  |  |  | All the tables as per design exist in database
Creating tables and dependencies
Developing code to implement various business functionalities
Capturing data from UI into database
Unit testing the code and dependencies
Documentation
10 | 1 | As a DB developer, I should be able to import,clean and load the data so that the data can be used as per business requirements |  |  | Able to store the raw data |  |  |  |  | Uploaded data from UI(.CSV files) is processed properly in to database tables
[5 empty] | Understanding the massage finders and designing the database | Clarity from clients
Implementing code to automate the cleaning of raw data and loading into actual tables
Collecting and loading the data
Unit testing the code and dependencies
Documentation
11 | 0 | As a guest, I should be able to view the public data visualization graphs created by admin and the summary, analysis tables,variable definition, credits related to these graphs |  |  | Allow admin to create data visualization graph, summary, analysis tables,variable definition and credits based on the available data and parameters
Allow any guest to view the data visualization graph created by admin
11 | 1 | As a guest, I should not be able to view the data visualization graphs of any private peer group |  |  | Admin should restrict the access to view peer group_data visualization graphs for any guest
12 | 1 | As an Admin User, I want Guest Users to be able to view and use public Peer Groups without having to register so that I can attract increased usage of the website. | Is this already covered?
12 | 2 | As an Admin User, I want Guest Users to have to register in order to create and use custom Peer Groups so that I can capture data about what users are interested in. | Is this already covered?
12 | 3 | As a Registered User, I want to load a previously created custom Peer Group so that I can continue my analysis from a previous visit to this website. |  |  | Build database query to retrieve saved peer group.
Develop UI and logic code
Unit test functionality
Test Functionality
Create User Manual Documentation'
12 | 4 | As a Registered User, I want to add or remove individual institutions to my custom Peer Group so that I can answer my unique research question. |  |  | Build database queries to retrieve peer groups, retrieve institutions, update peer groups, and delete peer groups.
Develop UI and logic code
Unit test functionality
Test Functionality
Create User Manual Documentation'
12 | 5 | As a Registered User, I want to add multiple institutions based on selected attributes to my custom Peer Group so that I can answer my unique research question. |  |  | Build database queries to retrieve peer groups, retrieve institutions, update peer groups, and delete peer groups.
Develop UI and logic code
Unit test functionality
Test Functionality
Create User Manual Documentation'
12 | 6 | As an Admin User, I want to create public Peer Groups so that Guest Users can easily analyze a group of similar institutions. |  |  | Create database query to create new public peer groups
Develop UI and logic code
Unit test functionality
Test Functionality
Create User Manual Documentation'
12 | 7 | As an Admin User, I want to add individual institutions to a public Peer Group so that Guest Users can answer common research questions. |  |  | Build database queries to retrieve peer groups, retrieve institutions, update peer groups, and delete peer groups.
Develop UI and logic code
Unit test functionality
Test Functionality
Create User Manual Documentation'
12 | 8 | As an Admin User, I want to add multiple institutions to a public Peer Group so that Guest Users can answer common research questions. |  |  | Build database queries to retrieve peer groups, retrieve institutions, update peer groups, and delete peer groups.
Develop UI and logic code
Unit test functionality
Test Functionality
Create User Manual Documentation'
13 | 0 | As a guest or registered user, I should be able to select public peer group and data should get filtered based on that peer group so that I can view the visualization graphs and summary related to that peer group |  |  | Admin should create public peer groups for all users (registered and guest)
| 1 | As a guest or registered user, I should be able to select parameters like resource, performance, year etc and data should get filtered on the basis of these parameters so that I can perform different analytics |  |  | Admin should provide an access to guest users to select public peer group
| 2 | As a guest or registered user, I should be able to view the change in graphs with the change in value of parameters so that I can do analysis based on the selected parameters value |  |  | Developing code for the given functionality
| 3 | As a guest or registered user, I should be able to view summary for the selected university so that I can view the complete information of that university |  |  | Testing the functionality
| 4 | As a guest or registered user, I should be able to view short summary for the selected parameters for that selected university so that I can view the x(resource),y(performance) coordinates value of the selected university on the graph |  |  | Preparing Document
| 5 | As a guest or registered user, I should be able to view peer analysis tables for the selected peer group so that I can compare different universities on the basis of different given fields
| 6 | As a guest or registered user, I should be able to view the change peer analysis tables with the change in peer index for the selected peer group so that I can compare different universities on the basis of different peer index
| 7 | As a guest or registered user, I should be able to view variable definitions and credits which will remain constant for any selected university so that I can understand each and every variable
| 8 | As a guest user, I should only be able to view and access public peer groups created by an admin so that I can also perform analytics and select already available peer group
| 9 | As a registered user, I should be able to select peers and save my peer group so that can perform analytics on that group later as well
| 10 | As a registered user, I should be able to load a saved peer group so that I can import any peer group and perform analytics on that group
| 11 | As a registered user, I should be able to save the selected performance metric and resource metric so that I can use it later
14 | 0 | As an admin, I should be able to maintain a backup log to avoid loss of information |  |  | Should be able to backup files and database prior to starting maintenance
14 | 1 | As an admin, I should be able to modify the content of the website to keep it up to date |  |  | Keep the contact information on the website up to date
Modify the layout or color of pages on the website
14 | 2 | As an admin, I should be able to grant user permissions to limit access to different user roles |  |  | Review users and passwords
Allow file and directory permissions
14 | 3 | As an admin, I should be able to increase content relevancy for Search Engine Optimization |  |  | Optimize and rename file names for Search Engines
Update meta keywords, page descriptions or titles for Search Engines
14 | 4 | As an admin, I should be able to keep a track of load time to maintain performance |  |  | Monitor visitor traffic on the website
Assess website performance based on load time
Test Contact forms to ensure they work as desired
Should be able to perform unit testing
Should be able to create documentation
15 | 0 | As an admin, I should be able to allow users to print the report/visualization for research/analysis and to share with higher management. |  |  | Build the module that allows a registered used to print the visualization.
Integrate the module to the application.
Test the module.
| 1 | As an admin, I should be able to print the reports/ data visualizations generated for research/analysis and to share with higher management. |  |  | Export the report/visualization that gets saved onto a document.
Provide basic print settings such as number of copies, layout etc.
Print the report/visualization with the default UNO Logo / Copyright statement
| 2 | As an registered user, I should be able to print the reports/ data visualizations generated for reserch/analysis and to share with higher management. |  |  | Export the report/visualization that gets saved onto a document.
Provide basic print settings such as number of copies, layout etc.
Print the report/visualization with the default UNO Logo / Copyright statement
| 3 | As an public user, I should be able to print the reports/ data visualizations generated for research/analysis and to share with higher management. |  |  | Export the report/visualization that gets saved onto a document.
Provide basic print settings such as number of copies, layout etc.
Print the report/visualization with the default UNO Logo / Copyright statement
16 |  | As an Admin I should be able to view the navigation Instructions and thumbnails so that I can maneuver through the application tool in the landing/Home page |  |  | Home page should have navigation and information about the features that the tool provides for each user type
16 |  | As an Registered User I should be able to view the navigation Instructions and thumbnails so that I can maneuver through the application tool in the landing/Home page |  |  | Design Mockups for the feature
16 |  | As an Guest User I should be able to view the navigation Instructions and thumbnails so that I can maneuver through the application tool in the landing/Home page |  |  | Come up with the text description/content and thumbnails to be displayed
16 |  |  |  |  | Test the thumbnails and links, if it works as expected
Document all the features and textual description of the feature
17 |  | As an Admin I should get appropriate error message upon selection of irrerevelant data(data which are out of scope) to notify me of the wrong search selection |  |  | List all the error message/pop-up's that needs to be displayed
17 |  | As an registered user I should get appropriate error message upon selection of irrerevelant (data which are out of scope) to notify me of the wrong search selection |  |  | List all the scenarios/voilations (Wrong Inputs) when the error msg needs to be displayed
17 |  | As an guest user I should get appropriate error message upon selection of irrerevelant (data which are out of scope) to notify me of the wrong search selection |  |  | Define the confinement/boundary of the data
Unit Test all the scenarios
17 |  | As an Admin I should be logged out of the Application tool, If not active for more than a specific amount of time so that the data/tool is secure |  |  | Design UI
17 |  | As a Registered User I should be logged out of the Application tool, If not active for more than a specific amount of time so that the data/tool is secure |  |  | Document the functionality and all the probable scenarios
Get appropriate data to test all the possible scenarios
18 | 1 | As an admin, I want to moderate, delete, reply to the comment to keep check on the abusive/irrelevant comments |  |  | install a comment system
18 | 2 | As an user, I should be able to comment, reply to other's comments.
18 | 3 | As a guest I should be able to view the comments written by others to know their opinion on the post.
18 | 4 | As an admin, I want to track the ip addresses of the commenters to avoid spam
18 | 5 | As an admin, I should be able to save the comments/data to track the data later to improve content.
18 | 6 | As an admin, I should be able to restrict/block ip addresses/users to avoid unauthorized users
19 | 1 | As an admin, I should be able track the views in real time to check how many users using the website at a single point of time. |  |  | An analytics tool needs to be configured.
19 | 2 | As an admin, I should be able to check the traffic sources to improve features that help more usage of the website.
19 | 3 | As an admin, I want to save daily/monthly/yearly analytics of the website to compare/check stats.
19 | 4 | As an admin, I want to allow/restrict the visibility of the website to a particular location to avoid the misusage of data.
20 | 0 | As an Admin I have to arrange user training |  |  | Arrange training sessions for users to get used to the new system.
Collect feedback for further improvements.
Implement the suggested changes